## APA Excel Gantt
Activity ID | Activity Name | Original Duration | Start | Finish | Duration Complete | Remaining Duration | % Complete | Total Float | Budgeted Labor Units | Cum Labor Units | % Cum
IS1101 | PFD (UFD) IFA | 20 | 2008-04-03 | 2008-04-30 | 20 | 0 | 100% | 0 | 20 | 20 | 4.706%
IS1102 | CLIENT REVIEW | 5 | 2008-05-01 | 2008-05-07 | 5 | 0 | 100% | 0 | 5 | 25 | 5.882%
IS1103 | EQUIP LIST IFA | 10 | 2008-05-08 | 2008-05-21 | 10 | 0 | 100% | 51 | 10 | 35 | 8.235%
IS1104 | EQUIP PROCESS DATASHEET IFA | 40 | 2008-05-08 | 2008-07-02 | 22.8 | 17.2 | 57% | 0 | 40 | 75 | 17.65%
IS1105 | PFD (UFD)RFE | 10 | 2008-05-08 | 2008-05-21 | 10 | 0 | 100% | 30 | 10 | 85 | 20%
IS1106 | P&ID IFA | 80 | 2008-05-08 | 2008-08-27 | 22.4 | 57.6 | 28% | 170 | 80 | 165 | 38.82%
IS1107 | EQUIP LIST RFE | 10 | 2008-05-22 | 2008-06-04 | 8 | 2 | 80% | 51 | 10 | 175 | 41.18%
IS1109 | PFD (UFD) IFD | 40 | 2008-05-22 | 2008-07-16 | 16 | 24 | 40% | 30 | 40 | 215 | 50.59%
IS1108 | EQUIP PROCESS DATASHEET RFE | 40 | 2008-07-03 | 2008-08-27 | 0 | 40 |  | 0 | 40 | 255 | 60%
IS1121 | EQUIPMENT MILESTONE | 5 | 2008-08-27 | 2008-08-27 | 0 | 5 |  | 0 | 0 | 255 | 60%
IS1110 | LINE LIST & SIZING IFA | 20 | 2008-08-28 | 2008-09-24 | 0 | 20 |  | 170 | 20 | 275 | 64.71%
IS1112 | CLIENT REVIEW | 5 | 2008-08-28 | 2008-09-03 | 0 | 5 |  | 170 | 5 | 280 | 65.88%
IS1113 | INST D/S PROCESS INPUT | 40 | 2008-08-28 | 2008-10-22 | 0 | 40 |  | 213 | 40 | 320 | 75.29%
IS1114 | P&ID RFE | 10 | 2008-09-04 | 2008-09-17 | 0 | 10 |  | 263 | 10 | 330 | 77.65%
IS1118 | PREL HAZOP | 5 | 2008-09-18 | 2008-09-24 | 0 | 5 |  | 263 | 5 | 335 | 78.82%
IS1116 | LINE LIST & SIZING IFD | 20 | 2008-09-25 | 2008-10-22 | 0 | 20 |  | 263 | 20 | 355 | 83.53%
IS1117 | P&ID IFD | 20 | 2008-09-25 | 2008-10-22 | 0 | 20 |  | 263 | 20 | 375 | 88.24%
IS1115 | INST D/S CAL & SIZING | 50 | 2008-10-23 | 2008-12-31 | 0 | 50 |  | 213 | 50 | 425 | 100%

## EULA
End User License Agreement | ©2016 Advanced Planning Analytics, All Rights Reserved.
1) This spreadsheet is provided on "an is" basis as freeware,
for NO consideration and with NO warranty actual or implied,
including but not limited to, fitness for purpose for any intended use.
2) There is NO warranty, actual or implied, that this
spreadsheet serves any purpose, useful or otherwise.
3) Using, copying, modifying and/or re-using modified versions
of this spreadsheet constitutes full acceptance and agreement
with the terms and conditions of this End User License Agreement (EULA).
4) This spreadsheet may be copied, modified and re-used by the
recipient provided the terms and conditions of supply described in
this EULA are agreed to in full.
5) Direct transfer of this spreadsheet or any products, electronic or otherwise, directly or indirectly
derived from this spreadsheet to other natural persons is permitted provided:
a) there is no payment or other consideration, either direct or indirect,
requested or made as part of the transfer; and
b) a copy of this EULA is included in the transfer; and
c) recipients agree to the terms and conditions of this EULA in full.
6) Transfer, either direct or indirect of this spreadsheet or any products, electronic or otherwise, directly
or indirectly, derived from this spreadsheet to persons other than natural persons is NOT permitted
unless the express permission of the license owner, Cesar Ramos, is obtained
prior to the proposed transfer taking place.
7) Placing this spreadsheet or any products, electronic or otherwise, directly or indirectly,
derived from this spreadsheet, into either an electronic, non electronic or other repository
of any other type, including but not limited to a corporate Intranet, public domain
website, public e-mail repository or any similar facility which will permit the free or
uncontrolled dissemination of this spreadsheet is expressly not permitted. Undertaking any
such action will constitute an express breach of the terms and conditions of this EULA.
8) This EULA is governed by the laws of the United States.
9) If any part of this EULA is found to be in conflict with the law, that
part shall be interpreted in its broadest meaning consistent with the law,
and no other parts of the EULA shall be affected.
10) If you do not accept the terms and conditions of this EULA in full
do not use and do not transfer this spreadsheet.
11) Delete the spreadsheet immediately, if you do not accept the terms
and conditions of this EULA in full.
©2016 Advanced Planning Analytics, All Rights Reserved.
EULA Excel Gantt Basic w/Progress : 27 Oct 2016